{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["封面","项目风险"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"封面","index":0,"n_rows":19,"n_cols":6,"rows_kept":19,"cut":false,"hidden":false,"merged":[[0,0,0,7],[22,0,22,7],[18,0,19,7],[1,0,5,7]]}
[]
["智慧水务一体化平台\n项目风险管理报告"]
{"$rows_empty":8}
[null,null,"文档版本号：","V1.0","文档编号："]
[null,null,"文档密级：","内部公开","归属部门/项目：","研发中心"]
[null,null,"编写人：","朱当义","生效日期：","2020-10-14"]
[]
[]
[]
[]
[]
["版权信息\n本文件涉及之信息，属深圳市华旭科技开发有限公司所有。\n    未经深圳市华旭科技开发有限公司允许，文件中的任何部分都不能以任何形式向第三方散发。    \n"]

{"sheet":"项目风险","index":1,"n_rows":9,"n_cols":12,"rows_kept":9,"cut":false,"hidden":false,"merged":[[2,0,2,3],[3,0,3,4],[0,0,1,11]]}
["项目风险管理报告"]
[]
["项目名称：智慧水务一体化平台",{"$nulls":4},"填表日期：2020-10-14",null," "]
["项目参与人数：",{"$nulls":4},"项目负责人：","朱当义"]
["编号","风险来源","风险类别","风险描述","可能发生阶段","风险影响","应对策略","缓解措施","责任人","风险状态","缓解措施执行情况","应急措施"]
[1,"内部","人力资源风险","项目组人员存在流动情况，招聘的人员可能无法按时到位","全部阶段","中","接受","1.人员离职需提前30天提交申请，在30天内需要补充相应人员；\n2.协调其他项目组的人员进行支援","朱当义","监控中，缓解措施正在实施","正在执行"]
[2,"内部","技术风险","项目组技术研发人员技术能力不足，设计开发的系统的性能无法满足市场需求；","详细设计","高","规避","1.招聘一个能掌握整体技术方向的技术经理，人员需尽快到位\n","彭迪/王杨杨","监控中","待确认","由信科进行技术援助"]
[3,"内部","公司组织风险","项目组研发人员有很多旧的项目需要维护，陆续有新的项目需求需要处理，会占用他们大量的时间，无法全力投入一体化平台的研发工作","全部阶段","高","规避","1.项目组的成员，必须把原有维护项目交接给其他人员处理；\n2.不属于项目组的需求，项目组研发成员有权力拒绝承接该需求任务","朱当义","监控中","待确认"]
[4,"内部","项目管理风险","项目组年度研发任务过于繁重，项目时间安排不合理，无法按时完成研发任务","全部阶段","高","减缓","1.在保证产品质量的前提下，能提前的工作任务尽量提前处理\n2.一周安排3天集体加班时间，加班时长2小时，项目开发期间所有的加班能计入调休","朱当义","监控中","待确认"]